## page-1-table-1
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
0 | Site Name | Joints Fully Removed | Joints Partially Removed | Joints Installed | Client Proposed Replacement Area | [6 empty] | Actual Replacement Area | [6 empty] | ILI |  | Completion Date
1 |  |  |  |  | RGW | Start Distance | Source Distance | RGW | End Distance | Source Distance | Length | RGW | Start Distance | Source Distance | RGW | End Distance | Source Distance | Length | Features Removed | Maximum Depth
2 | 2019-433-1 | 1 | 2 | 1 | 433 | 0.00 m | 5968.26 m | 433 | 17.00 m | 5985.26 m | 17.00 m | 443 | -0.55 m | 5967.71 m | 443 | 17.17 m | 5985.43 m | 17.72 m | 15 | 45% | 20-Nov-19
3 | 2019-441-2 | 4 | 2 | 4 | 441 | -18.25 m | 6064.93 m | 441 | 51.75 m | 6134.93 m | 70.00 m | 441 | -18.43 m | 6064.75 m | 441 | 52.00 m | 6135.18 m | 70.43 m | 38 | 49% | 20-Nov-19
4 | 2019-456-3 | 3 | 2 | 4 | 456 | 0.00 m | 6300.41 m | 456 | 59.25 m | 6359.66 m | 59.25 m | 456 | -0.50 m | 6299.91 m | 456 | 59.83 m | 6360.24 m | 60.33 m | 99 | 49% | 21-Nov-19
5 | 2019-875-4 | 2 | 2 | 3 | 875 | 0.00 m | 12979.80 m | 875 | 44.50 m | 13024.30 m | 44.50 m | 875 | -0.20 m | 12979.60 m | 875 | 44.75 m | 13024.55 m | 44.95 m | 95 | 49% | 21-Nov-19
6 | 2019-1593-5 | 4 | 2 | 4 | 1593 | 0.00 m | 24600.08 m | 1593 | 80.00 m | 24680.08 m | 80.00 m | 1593 | -0.15 m | 24599.93 m | 1593 | 79.46 m | 24679.54 m | 79.61 m | 27 | 60% | 20-Nov-19
7 | 2019-2906 Tee Removal | 1 | 2 | 1 | 2906 | 0.00 m | 44500.03 m | 2906 | 0.35 m | 44500.38 m | 0.35 m | 2906 | -0.92 m | 44499.11 m | 2906 | 1.25 m | 44501.28 m | 2.17 m | 1 Tee |  | 21-Nov-19
8 | 2019-2924-6 | 1 | 2 | 1 | 2924 | 0.00 m | 44659.83 m | 2924 | 13.75 m | 44673.58 m | 13.75 m | 2924 | -0.20 m | 44659.63 m | 2924 | 13.87 m | 44673.70 m | 14.07 m | 26 | 67% | 19-Nov-19
9 | 2019-2939-7 | 10 | 2 | 7 | 2939 | 0.00 m | 44773.35 m | 2939 | 119.04 m | 44892.39 m | 119.04 m | 2939 | -0.42 m | 44772.95 m | 2939 | 119.45 m | 44892.80 m | 119.87 m | 246 | 65% | 20-Nov-19
10 | 2019-2973 Tee Removal | 1 | 2 | 1 | 2973 | 0.00 m | 45162.15 m | 2973 | 0.36 m | 45162.51 m | 0.36 m | 2973 | -0.87 m | 45161.28 m | 2973 | 4.12 m | 45166.27 m | 4.99 m | 20 | 44% | 21-Nov-19
11 | 2019-2983-8 | 2 | 2 | 2 | 2983 | 0.00 m | 45260.09 m | 2983 | 24.25 m | 45284.34 m | 24.25 m | 2983 | -0.21 m | 45259.88 m | 2983 | 24.40 m | 45284.49 m | 24.61 m | 83 | 60% | 20-Nov-19
12 | 2019-3151-9 | 4 | 2 | 3 | 3151 | -1.25 m | 47127.34 m | 3151 | 47.75 m | 47176.34 m | 49.00 m | 3151 | -1.40 m | 47127.19 m | 3151 | 48.15 m | 47176.74 m | 49.55 m | 52 | 62% | 20-Nov-19
13 | 2019-3158-10 | 2 | 2 | 2 | 3158 | -0.75 m | 47209.12 m | 3158 | 22.25 m | 47232.12 m | 23.00 m | 3158 | -1.27 m | 47208.60 m | 3158 | 24.23 m | 47234.10 m | 25.50 m | 98 | 58% | 20-Nov-19
14 | 2019-3260-11 | 2 | 2 | 2 | 3260 | -6.25 m | 48342.72 m | 3260 | 16.50 m | 48365.47 m | 22.75 m | 3260 | -6.30 m | 48342.67 m | 3260 | 16.74 m | 48365.71 m | 23.04 m | 25 | 64% | 20-Nov-19
15 | Totals | 37 | 26 | 35 | [6 empty] | 523.25 m | [6 empty] | 536.84 m | 824 | 67%
16 | Site Summary Comments
17 | Tee removal sites were done by operations in Olds Ab under the AFE: 10A05673